## Taulukko1
LIITE 4. Tabledom Alfa projekti - toiminnallinen sisältö - Codemate Oy
Id | Requirement | Notes | Estimation | Estimation
(man-days)
| System, Security,Scalability | Set up Operating System, Web Server, Database Server, and other base applications. | 2
|  | Set up automated deployment system. |  | 1.5days
Set up the application framework and configuration.
| User Interface,Interactivity | Design the HTML5 Bootstrap theme based on the UI design (.PSD file) | 5
|  | The UI is responsive upwards to Full HD resolution and downwards to iPad resolution. |  | 4 days
Integrate into the system, including menu items and main site structure, sitemap, etc.
Design and implement the various fixed page layouts.
| Actors, Data Model | Implement the data model for all actors. | 1 | 1 days
Implement the data model for all entities: Game Tags and Game Categories
| Launch [as anonymous] | The launch screen has basically the Customer logo and buttons to login, register or continue to page as anonymous. | 0
| Login [as anonymous] | If previously registered, Anonymous will be able to login using his username / email and his password. Note that logging in is not required to access the home page and other functionality. | 1 | 1 day
|  | There will be a link to register. There will also be a "Forgot my password" link that sends an email to the user with a link which he can use to reset his password. |  | 1 day
| Register [as anonymous] | Registering has basically the same functionality as "Editing Profile", but also includes choosing a unique username, unique email, and a password (with confirm password field). The system will then send a confirmation email which contains a link that the user must visit in order to confirm his email address and account, and get automatically logged into the web application. | 1 | 2days
|  | The functionality included from "Edit Profile" are full name, nickname, home location (on map), avatar image upload, and game tags. |  | 1 day
| View Public Profile [as anonymous/user/admin] | Every user's profile is publicly viewable by Anonymous. It includes the player nickname, avatar image, game tags (by category), age, and location on map. It does NOT include the player full name or email address. | 0.5 | 1 day
|  | If the visiting user is logged in, he also sees a contact button which he can use to send a message to the user whose profile page he is visiting. There's also Add to Contacts - button which adds the player to the contact list of the user. |  | 1 day
| Connect (Social) [as user/admin] | The user-to-user messages are handled inside the system in the "Connect" page, which lists all messages in chronological order, related to the registered user. The user can reply to any message directly from the post in the Connect page. |  | 2.5 days
Tabs for Connect left panel : Players, Groups, Events, Tournament (only Players is enabled in alfa-version - it shows the user's contact list).
|  | Search contacts: Show own Contacts in the search results first, then other users after that. | 0.5
| View Personal Profile [as user/admin] | Your own profile page, when logged in, will show everything your public profile has, but also include the private information: full name and email address. |  | .5 days
| Update Personal Profile (My Profile) [as user/admin] | The Personal profile area is divided into TWO PAGES: My Profile and My Games. | 1
| Update Personal Profile (My Games) [as user/admin] | All personal information can be changed in My Profile page, including your password and email address. Also home location and profile picture is set here. If changing your email address, you must "re-verify" it by getting another email with a verification link. | 1 | 1 day
|  | User can add games by typing to a search field. As the user types, suggestions on existing tags are given and can be chosen.When a game is chosen it automatically appears to the user's profile, under the right category |  | 1 day
|  | If a game doesn't exist, user can create the game tag by pressing "Add a new game" button and selecting the game category. There are four game categories: board, role, card and miniature. All tags must belong to one category. |  | 1 day
| Games Listing [as anonymous/user/admin] | Once added, game tags cannot be edited or removed. Only Admin can delete tags or change their name or category. | 1
|  | All the games tags are listed by category. Any user (that is logged in) can add new tags by pressing the + button next to the category title. There are four game categories: board, role, card and miniature. All tags must belong to one category. |  | 1day
|  | Once added, game tags cannot be edited or removed. Only Admin can delete tags or change their name or category. |  | 1 day
| Users Listing on Map [as anonymous/user/admin] | Admin can merge two tags, so that users with the deleted tag will have the new tag. (i.e users can be moved from one tag group to another). Use case: same game has two different tags "Monopoli" and "Monopoly" and one of these is deleted. | 1 | 1day
| Users Search by Game and Location [as anonymous/user/admin] | If the user is logged in, the map is shown centred on the user's location, and nearby users are pinpointed on the map with player icons. When hovered over the person icon, a popup will show player avatar image, nickname, and games. When clicked, the user public profile page is opened. | 3 | 2 days
|  | The main page of the service. Has a map and search filters. Map shows search results (player icons on map) and filters are used for filtering players by game tags. |  | 1 day
|  | Integration of Google Maps map element to the search page. Users are shown on the map, based on their home location. |  | 1 day
|  | Filters: search by game tags, search by game category. Selected filters are saved for the session. Reset when logout or exit. Reset all filters -button |  | 1day
The search results are filtered simultaneously as the user writes. If there are a lot of results in the game list - there's a scroll bar in the box.
| User Management [as admin] | When hovered over the person icon, a popup will show player avatar image, nickname, and games. When clicked, the user public profile page is opened in the Connect page. | 1 | 2 days
The admin can see a paginated list of users in the system. This will include ALL information from the user profile, including name, nickname, email, location, game tags, and avatar image.
| Game Management [as admin] | The admin can click "View" to go to the user's public profile page, or "Delete" to remove him. | 1
|  | The admin can see a paginated list of game tags in the system. This will include ALL information about the tag, including name, category, and user count. |  | 1days
| Analytics | The admin can click "Edit" to modify the tag name or category, or "Delete" to remove it. When a tag is modified, the user's who assigned that tag to themselves are not changed. They will continue to see the edited tag assigned to them. |  | 1 days
| Create | Google Analytics | 5
|  | Create -menu item will have a dropdown menu with disabled subitems: Group, Event, Tournament. | 3
Others like creating menu and integration html into the application
25 man-days